## Overview
Test Plan: Sprint 1 & 2
Tester: | Noel Romey
Date: | 02/03/2026
App Version: | 4.1.10
Test Radio(s): | Flex 6300 Remote
Prerequisites
NVDA or JAWS installed and running
At least one FlexRadio available (local or remote)
SmartLink account credentials available
Fresh install or cleared config (optional)
Summary
Sprint | Total | Passed | Failed | Blocked
Sprint 1 | 10
Sprint 2 | 17
TOTAL

## Sprint 1
# | Test Case | Steps | Expected | Pass/Fail | Notes
1.1 | First-time login | Click Remote > Add Account > Log in | Auth0 login page appears in WebView2, login succeeds, account saved
1.2 | Account appears in selector | After login, open Remote again | Saved account shown in list with email
1.3 | Connect with saved account | Select saved account > Connect | Connects without re-entering credentials
1.4 | Token refresh | Wait for token expiry (or restart app after ~1hr) | Silent refresh, no login prompt
1.5 | Refresh failure | (Hard to test) Invalidate refresh token | Prompts for re-authentication
1.6 | Rename account | Right-click account > Rename | Can change display name, saved
1.7 | Delete account | Right-click account > Delete | Account removed from list
1.8 | Multiple accounts | Add second SmartLink account | Both accounts shown, can switch
1.9 | Account selector with NVDA | Tab through account selector | All controls announced, no & characters read
1.10 | Auth completing announcement | Complete login flow with NVDA | Completing authentication announced

## Sprint 2
# | Test Case | Steps | Expected | Pass/Fail | Notes
2.1 | Set auto-connect (local) | RigSelector > Right-click local radio > Auto-Connect Settings > Enable > Save | Settings dialog shows, radio marked [AutoConnect] in list
2.2 | Set auto-connect (remote) | Same as above for remote radio | Works same as local
2.3 | Auto-connect on startup | Set auto-connect, restart app | App connects silently, no RigSelector shown
2.4 | Single radio constraint | Try to set auto-connect on Radio B when A has it | Confirmation dialog: Switch to Radio B?
2.5 | Low bandwidth saved | Enable auto-connect + Low BW, restart | Connects with low bandwidth mode
2.6 | Disable global auto-connect | Uncheck Enable auto-connect on startup | RigSelector shown on next startup
2.7 | Re-enable global | Check the checkbox again, restart | Auto-connect works again
2.8 | Radio offline dialog | Set auto-connect, turn off radio, start app | Friendly dialog: [Radio] is not available with 4 options
2.9 | Try Again | Click Try Again in offline dialog | Retries connection
2.10 | Disable Auto-Connect | Click Disable in offline dialog | Auto-connect cleared, RigSelector shown
2.11 | Choose Another Radio | Click Choose Another | RigSelector opens
2.12 | Cancel | Click Cancel | Dialog closes, app stays disconnected
2.13 | Switch while connected | Radio menu > Select Rig (while connected) | Disconnects current, opens RigSelector
2.14 | Connect to different radio | After disconnect, select different radio | Connects to new radio without restart
2.15 | Login button hidden | Open RigSelector | Login button not visible
2.16 | Login button not in tab order | Tab through RigSelector | Cannot tab to Login button
2.17 | Auto-connect indicator | Set auto-connect on a radio | Radio shows [AutoConnect] prefix in list
2.18 | Low BW indicator | Toggle Low BW for a radio | Radio shows [LowBW] prefix in list
2.19 | Connecting to announced | Connect to radio with NVDA | Connecting to [RadioName] spoken
2.20 | Connected to announced | Connection completes | Connected to [RadioName] spoken
2.21 | Disconnecting announced | Disconnect via Select Rig | Disconnecting from [RadioName] spoken
2.22 | Offline announced | Trigger offline dialog | [RadioName] is offline spoken
2.23 | Auto-connect set announced | Enable auto-connect | Auto-connect set for [RadioName] spoken
2.24 | Global toggle announced | Check/uncheck global checkbox | Auto-connect on startup enabled/disabled spoken
2.25 | Settings dialog accessible | Open Auto-Connect Settings dialog | Radio name, checkboxes, buttons all announced

## Issues Found
# | Test | Issue Description | Severity | Status